## Core Plan
This assignment is a miniature end-to-end modern data stack for a recommendation system, not just a modelling exercise. The mandatory scope runs across: - business/problem formulation - multi-source ingestion - raw storage - data validation - cleaning/EDA - transformation - feature management -data versioning/lineage -model training/evaluation -orchestration-documentation -demo video. The rubric also makes the priority clear: Data Pipeline Implementation = 40%, Feature Store & Versioning = 20%, Problem Formulation = 15%, Documentation & Demo = 15%, and Model Training & Evaluation = 10%. So the safest execution strategy is completeness, modularity, logs, reproducibility, and evidence capture, not over-optimizing the recommender itself.
Low-risk implementation choice
Layer | Recommended choice | Reason
Ingestion | Python scripts (pandas, requests) | Fastest to implement and easy to demonstrate
Raw storage | Local filesystem data lake with partitions | Meets requirement without cloud complexity
Validation | pandas + Great Expectations / custom checks | Easy PDF-quality DQ reporting
Curated storage | SQLite/Postgres | Enough for SQL schema + transformed tables
Feature store | Custom lightweight registry | Lower risk than forcing Feast if team is unfamiliar
Versioning | Git + DVC | Satisfies data versioning and lineage requirement
Experiment tracking | MLflow | Clean run metadata, metrics, artifacts
Orchestration | Prefect or Airflow | Prefect is lighter locally; Airflow is more traditional
A practical interpretation of “near-real-time” for an assignment is frequent scheduled mini-batches, not true streaming infrastructure.

## Stories
Parallel execution rule To keep all 4 people productive simultaneously, the team should use a contract-first / mock-first approach: Lock schemas, interfaces, folder conventions, and metric definitions on Day 1. Let downstream owners build against sample/mock data shaped to the agreed contract. Integrate twice only: once at module level, once at end-to-end pipeline level. That avoids one person waiting for another person’s entire sprint to finish. How the workflow runs from start to finish Phase 1 — Contract lock, no waiting Run REC-1 to REC-4 in parallel. Output: one shared “contract pack” containing business scope, schemas, SQL blueprint, metric definitions, and interface contracts. Phase 2 — Data acquisition and infrastructure scaffolding Run REC-5, REC-6, REC-7, REC-8 in parallel. Output: ingestion scripts, raw storage structure, logs, MLflow setup. Phase 3 — Core data pipeline build Run REC-9, REC-10, REC-11, REC-13, REC-14, REC-12 in parallel, all against mock/sample data first and real outputs later. Output: validation, cleaned data, transformed tables, feature registry, DVC lineage, trained baseline model. Phase 4 — End-to-end assembly Run REC-15 while modules are being finished, using stub tasks first and full module wiring later. Then run REC-16 for final packaging, report, screenshots, and demo evidence. This structure avoids the bad pattern where: Person3 waits for Person2’s “finished dataset” Person4 waits for Person3’s “finished features” Person1 waits for all three people before starting orchestration Instead, everyone starts immediately on stable interfaces, not finished outputs. | Story ID | Story Title | Owner | Story Points | Assignment coverage | Steps / definition of done | Dependency posture
| REC-1 | Define problem statement, KPIs, outputs, and scope note | Person1 | 2 | Task 1 | 1. Frame RecoMart use case as personalized top-N recommendation for conversion/cross-sell.2. Define entities: users, items, interactions, transactions, product metadata, external scores.3. Define expected outputs: clean EDA dataset, transformed feature tables, trained model, inference interface.4. Finalize evaluation metrics: Precision@K, Recall@K, NDCG.5. Draft report section for problem formulation. | No blocker; starts immediately
| REC-2 | Define source schemas and validation specification | Person2 | 2 | Task 1, Task 4 | 1. Define schemas for clickstream CSV, transactions CSV, product metadata API, external enrichment API.2. Document mandatory/optional fields, data types, primary keys, timestamp formats, rating/value ranges.3. Define validation rules for nulls, duplicates, schema mismatch, invalid ranges, malformed timestamps.4. Publish schema contract for the team. | No blocker; starts immediately
| REC-3 | Design curated data model and transformation blueprint | Person3 | 2 | Task 6 | 1. Design raw → prepared → transformed flow.2. Create SQL schema for users, items, interactions, item_features, user_features, recommendation_candidates.3. Define join keys, surrogate keys if needed, and transformation logic.4. Publish ER-style blueprint / schema note. | No blocker; starts immediately
| REC-4 | Define modelling protocol, evaluation plan, and inference contract | Person4 | 2 | Task 1, Task 9 | 1. Choose minimum viable model strategy: collaborative filtering baseline, with optional content features if time permits.2. Define train/validation/test split logic.3. Freeze model input format and recommend(user_id, k) output contract.4. Define MLflow logging fields: params, metrics, artifacts, run name. | No blocker; starts immediately
| REC-5 | Build batch ingestion for clickstream and transaction files | Person1 | 4 | Task 2, Task 3 | 1. Create ingestion scripts for CSV/file-based sources.2. Add periodic execution support (manual scheduler hook or orchestrator callable).3. Implement retry/error handling for corrupt/missing files.4. Write success/failure logs with timestamps.5. Land outputs into partitioned raw storage. | Depends only on contract from REC-1/2, not on completed upstream data
| REC-6 | Build API ingestion for product catalog and external scores | Person2 | 4 | Task 2, Task 3 | 1. Create REST API fetchers for product metadata and external popularity/sentiment source.2. Handle pagination/timeouts/retries.3. Persist raw JSON/CSV snapshots into partitioned storage.4. Log API response status and ingestion outcome.5. Preserve sample responses for documentation/demo. | Depends only on REC-2 contract
| REC-7 | Finalize raw data lake layout and storage documentation | Person1 | 2 | Task 3 | 1. Define folder structure such as data/raw/source=<src>/dt=<date>/hr=<hour>/....2. Define file naming convention and audit fields.3. Write storage README/config note.4. Ensure all ingestion scripts land into this structure consistently. | Can proceed in parallel with REC-5 and REC-6
| REC-8 | Set up MLflow tracking and experiment metadata conventions | Person4 | 2 | Task 9 | 1. Initialize MLflow locally.2. Define artifact folders for model, metrics, plots, params, report snapshots.3. Run a dummy experiment to verify tracking.4. Document how training scripts should log runs. | Independent; can start immediately
| REC-9 | Implement automated validation, profiling, and quarantine flow | Person2 | 3 | Task 4 | 1. Code schema checks, duplicate checks, null checks, range checks, timestamp format checks.2. Generate validation summary report (CSV/HTML/PDF-ready).3. Route failed files/rows to quarantine folder.4. Publish DQ metrics required for final report. | Can start on sample data first; real data swapped in later
| REC-10 | Implement cleaning, preparation, and EDA outputs | Person2 | 3 | Task 5 | 1. Handle missing interactions and malformed records.2. Encode categorical variables such as category/brand.3. Normalize numeric/time-derived variables.4. Produce EDA plots: interaction frequency, item popularity, sparsity, basic distribution charts.5. Export prepared dataset for downstream transformation/modeling. | Can begin with mocked ingested data shaped to contract
| REC-11 | Build SQL transformations and engineered feature tables | Person3 | 4 | Task 6 | 1. Implement SQL/scripts for curated and transformed layers.2. Create features such as user activity frequency, average rating per user/item, recency features, co-occurrence/similarity candidates.3. Populate structured DB/warehouse tables.4. Write feature logic summary. | Uses REC-3 contract; can start on synthetic/prepared sample data
| REC-12 | Train baseline recommender, evaluate, and expose inference stub | Person4 | 5 | Task 9 | 1. Train at least one required recommendation model.2. Evaluate using Precision@K, Recall@K, NDCG.3. Log runs in MLflow with parameters/metrics/artifacts.4. Create simple inference interface or script for top-K recommendations.5. Produce model performance summary for the report. | Can start with synthetic prepared data and replace with real pipeline output at integration
| REC-13 | Implement feature store / metadata registry and retrieval demo | Person3 | 4 | Task 7 | 1. Build simple feature registry: feature name, source, transformation, version, entity, retrieval path.2. Support retrieval for training and inference by version/entity key.3. Demonstrate feature lookup through notebook/script.4. Document metadata clearly for submission. | Works in parallel with REC-11; integration later
| REC-14 | Set up data versioning and lineage workflow with DVC | Person3 | 2 | Task 8 | 1. Initialize DVC tracking for raw, prepared, and transformed datasets.2. Define dataset version naming and metadata conventions.3. Document lineage: source → ingestion date → validation → transformation → feature version.4. Capture repository structure screenshots/evidence. | Starts as soon as first sample datasets exist
| REC-15 | Build orchestration flow with logging and failure handling | Person1 | 4 | Task 10 | 1. Create Prefect/Airflow DAG: ingestion → validation → preparation → transformation → feature store → training.2. Use stub tasks first, then wire final modules.3. Add logging, task status, and failure visibility.4. Capture successful run logs/screenshots. | Stub-first, so not blocked; final wiring at integration
| REC-16 | Compile final report, demo script/video plan, and submission package QA | Person4 | 3 | Documentation, demo, final zip | 1. Assemble evidence from all stories into final PDF sections.2. Build final demo sequence: architecture, ingestion, validation, feature flow, model, orchestration run.3. Create submission checklist for code, PDFs, logs, screenshots, video, zip.4. Run final QA against rubric. | Continuous evidence gathering; final assembly at the end

## Diagram
Blue: input source systems Green: ingestion and raw landing Yellow: validation, quality, and preparation Purple: transformation and feature management Grey: governance, versioning, and lineage Pink: model training, evaluation, and inference Orange: orchestration and monitoring